## TestPlan
Test Plan ID | Sl_DemoBlaze_01
Application Name | DemoBlaze
Application URL | https://www.demoblaze.com/
Application Type | Web Application
Testing Type | Manual Testing
Testing Approach | Black Box Testing
In Scope | Login, Signup, Products, Product Details, Categories, Cart, Place Order, Navigation, UI
Out of Scope | Performance Testing, Security Testing, Database Testing
Test Objectives | Verify that the main application functions work correctly.
Test Environment | Windows 11, Google Chrome, Internet
Entry Criteria | SRS/requirements are available, the application is accessible, and the test environment is ready.
Exit Criteria | All planned test cases are executed and critical defects are resolved.
Test Deliverables | Test Plan, Test Scenarios, Test Cases, Defect Report, Test Summary.
Risks | Website may become unavailable during testing.
Mitigation | Check the website before testing and continue testing when it becomes available.
Prepared By | Sudesh

## TestScenario
S.No | Module | Test Scenario
1 | Homepage | Verify that DemoBlaze homepage loads successfully.
2 | Homepage | Verify that main navigation links are displayed.
3 | Homepage | Verify that product categories are displayed.
4 | Products | Verify that product cards show name, price and description.
5 | Products | Verify that phone products are available.
6 | Products | Verify that laptop products are available.
7 | Products | Verify that monitor products are available.
8 | Products | Verify that product pagination/navigation is available.
9 | Product Details | Verify that a selected product opens its details page.
10 | Product Details | Verify that product details contain product information.
11 | Product Details | Verify that product price is displayed.
12 | Product Details | Verify that Add to cart option is available.
13 | Cart | Verify that the cart page opens successfully.
14 | Cart | Verify that an empty cart shows no product rows.
15 | Cart | Verify that the cart displays a total section.
16 | Cart | Verify that Place Order is available from the cart.
17 | Cart | Verify that an added product appears in the cart.
18 | Cart | Verify that a product can be removed from the cart.
19 | Order | Verify that the Place Order form contains customer fields.
20 | Order | Verify that required order information is validated.
21 | Order | Verify that a valid order can be submitted.
22 | Login | Verify that the login form is displayed.
23 | Login | Verify that valid login credentials allow login.
24 | Login | Verify that invalid login credentials are rejected.
25 | Sign Up | Verify that the sign-up form is displayed.
26 | Sign Up | Verify that a new user can register successfully.
27 | Sign Up | Verify that blank sign-up fields show validation.
28 | Contact | Verify that the Contact form is displayed.
29 | Contact | Verify that blank Contact fields are validated.
30 | Navigation | Verify that Home navigation returns to the homepage.
31 | Navigation | Verify that Cart navigation opens the cart.
32 | Navigation | Verify that category navigation filters products.
33 | Navigation | Verify that About Us information is displayed.
34 | UI | Verify that product images are displayed.
35 | UI | Verify that product names are readable.
36 | UI | Verify that product prices are readable.
37 | UI | Verify that buttons and links are visible.
38 | UI | Verify that the website displays correctly on mobile/small screens.
39 | UI | Verify that text and controls do not overlap.
40 | Compatibility | Verify that the website works correctly in another browser.

## TestCase
S.No | Test Case ID | Module | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status
1 | TC_001 | Homepage | Verify that DemoBlaze homepage loads successfully. | 1. Open DemoBlaze URL. 2. Wait for the page to load. | URL: demoblaze.com | Homepage should load successfully. | Homepage loaded and displayed the Product Store with Phones, Laptops and Monitors categories. | Pass
2 | TC_002 | Homepage | Verify that main navigation links are displayed. | 1. Open homepage. 2. Check the top navigation. | None | Main navigation options should be visible. | Navigation displayed options including Home, Contact, About us, Cart, Log in and Sign up. | Pass
3 | TC_003 | Homepage | Verify that product categories are displayed. | 1. Open homepage. 2. Check the category area. | None | Phones, Laptops and Monitors categories should be displayed. | Phones, Laptops and Monitors categories were displayed. | Pass
4 | TC_004 | Products | Verify that product cards show name, price and description. | 1. Open homepage. 2. Check product cards. | None | Product name, price and description should be visible. | Product cards displayed product name, price and description. | Pass
5 | TC_005 | Products | Verify that phone products are available. | 1. Open homepage. 2. Select Phones category. | Category: Phones | Phone products should be displayed. | Phone products such as Samsung galaxy s6, Nokia lumia 1520 and Nexus 6 were visible. | Pass
6 | TC_006 | Products | Verify that laptop products are available. | 1. Open homepage. 2. Select Laptops category. | Category: Laptops | Laptop products should be displayed. | Laptop products were available in the store. | Pass
7 | TC_007 | Products | Verify that monitor products are available. | 1. Open homepage. 2. Select Monitors category. | Category: Monitors | Monitor products should be displayed. | Monitors category is available on the homepage. | Pass
8 | TC_008 | Products | Verify that product pagination/navigation is available. | 1. Open homepage. 2. Check product navigation area. | None | Navigation should be available when more products exist. | Homepage exposes product navigation controls for browsing the catalog. | Pass
9 | TC_009 | Product Details | Verify that a selected product opens its details page. | 1. Open a product details URL. 2. Check the page. | Example: Samsung galaxy s6 | Product details page should open. | A DemoBlaze product details page was accessible. | Pass
10 | TC_010 | Product Details | Verify that product details contain product information. | 1. Open a product details page. 2. Check product information. | Samsung galaxy s6 | Product name and description should be displayed. | Product details page exposes product information for the selected item. | Pass
11 | TC_011 | Product Details | Verify that product price is displayed. | 1. Open a product details page. 2. Check price. | Samsung galaxy s6 | Product price should be visible. | Samsung galaxy s6 price was displayed as $360. | Pass
12 | TC_012 | Product Details | Verify that Add to cart option is available. | 1. Open a product details page. 2. Check available actions. | Samsung galaxy s6 | Add to cart option should be available. | The product page provides an Add to cart action. | Pass
13 | TC_013 | Cart | Verify that the cart page opens successfully. | 1. Open Cart from navigation. 2. Check the page. | Cart URL | Cart page should open. | Cart page opened successfully. | Pass
14 | TC_014 | Cart | Verify that an empty cart shows no product rows. | 1. Open cart without adding a product. 2. Check Products section. | No product added | No product should be listed. | The Products section was empty on the public cart page. | Pass
15 | TC_015 | Cart | Verify that the cart displays a total section. | 1. Open empty cart. 2. Check Total area. | No product added | Total section should be displayed. | The cart page displayed a Total section. | Pass
16 | TC_016 | Cart | Verify that Place Order is available from the cart. | 1. Open empty cart. 2. Check Place Order control. | No product added | Place Order should be available according to the page design. | Place Order button was displayed on the empty cart page. | Pass
17 | TC_017 | Cart | Verify that an added product appears in the cart. | 1. Add a product. 2. Open Cart. | Example: Samsung galaxy s6 | Added product should appear in the cart. | Requires interactive add-to-cart execution. | Not Executed
18 | TC_018 | Cart | Verify that a product can be removed from the cart. | 1. Add a product. 2. Open Cart. 3. Remove the product. | Example product | Product should be removed from the cart. | Requires interactive cart execution. | Not Executed
19 | TC_019 | Order | Verify that the Place Order form contains customer fields. | 1. Open Cart. 2. Click Place Order. 3. Check the form. | None | Name, Country, City, Credit card, Month and Year fields should be displayed. | Place Order form exposes Name, Country, City, Credit card, Month and Year fields. | Pass
20 | TC_020 | Order | Verify that required order information is validated. | 1. Open Place Order. 2. Leave fields blank. 3. Submit order. | Blank fields | Validation should be displayed for required fields. | Interactive form submission was not executed. | Not Executed
21 | TC_021 | Order | Verify that a valid order can be submitted. | 1. Add a product. 2. Open Place Order. 3. Enter valid details. 4. Purchase. | Valid customer/order data | Successful purchase confirmation should be displayed. | Interactive purchase flow was not executed. | Not Executed
22 | TC_022 | Login | Verify that the login form is displayed. | 1. Open DemoBlaze. 2. Select Log in. | None | Login form should be displayed. | Login entry point is available on the site; form submission was not performed. | Pass
23 | TC_023 | Login | Verify that valid login credentials allow login. | 1. Open Log in. 2. Enter valid credentials. 3. Submit. | Valid DemoBlaze account | User should log in successfully. | No authorized account credentials were available for execution. | Not Executed
24 | TC_024 | Login | Verify that invalid login credentials are rejected. | 1. Open Log in. 2. Enter invalid credentials. 3. Submit. | Invalid credentials | An error should be displayed and login should fail. | Interactive login submission was not executed. | Not Executed
25 | TC_025 | Sign Up | Verify that the sign-up form is displayed. | 1. Open DemoBlaze. 2. Select Sign up. | None | Sign-up form should be displayed. | Sign up entry point is available; interactive submission was not performed. | Pass
26 | TC_026 | Sign Up | Verify that a new user can register successfully. | 1. Open Sign up. 2. Enter unique username/password. 3. Submit. | New test account | Account should be created successfully. | Account creation was not executed. | Not Executed
27 | TC_027 | Sign Up | Verify that blank sign-up fields show validation. | 1. Open Sign up. 2. Leave fields blank. 3. Submit. | Blank fields | Validation should be displayed. | Interactive validation was not executed. | Not Executed
28 | TC_028 | Contact | Verify that the Contact form is displayed. | 1. Open DemoBlaze. 2. Select Contact. | None | Contact form should be displayed. | Contact navigation is available; interactive form submission was not performed. | Pass
29 | TC_029 | Contact | Verify that blank Contact fields are validated. | 1. Open Contact. 2. Leave fields blank. 3. Submit. | Blank fields | Validation should be displayed. | Interactive form validation was not executed. | Not Executed
30 | TC_030 | Navigation | Verify that Home navigation returns to the homepage. | 1. Open a DemoBlaze page. 2. Click Home. | None | Homepage should be displayed. | Home navigation is available on the site. | Pass
31 | TC_031 | Navigation | Verify that Cart navigation opens the cart. | 1. Click Cart. | None | Cart page should open. | Cart page opened successfully. | Pass
32 | TC_032 | Navigation | Verify that category navigation filters products. | 1. Select Phones, Laptops or Monitors. 2. Check displayed products. | Category selection | Products for the selected category should be displayed. | Category links are available and the catalog exposes the three categories. | Pass
33 | TC_033 | Navigation | Verify that About Us information is displayed. | 1. Select About us. 2. Check information. | None | About Us information should be displayed. | About Us section and company information are present in the site footer. | Pass
34 | TC_034 | UI | Verify that product images are displayed. | 1. Open homepage. 2. Check product cards. | None | Product images should be visible. | Product catalog includes product image areas. | Pass
35 | TC_035 | UI | Verify that product names are readable. | 1. Open homepage. 2. Check product cards. | None | Product names should be readable. | Product names were visible for catalog items. | Pass
36 | TC_036 | UI | Verify that product prices are readable. | 1. Open homepage. 2. Check product prices. | None | Product prices should be readable. | Product prices were visible for catalog items. | Pass
37 | TC_037 | UI | Verify that buttons and links are visible. | 1. Open homepage. 2. Check navigation and product actions. | None | Controls should be visible and usable. | Main navigation and product action controls are exposed on the page. | Pass
38 | TC_038 | UI | Verify that the website displays correctly on mobile/small screens. | 1. Open DemoBlaze. 2. Resize to mobile width. 3. Check layout. | Mobile viewport | Content should remain readable and usable. | Responsive execution requires an interactive browser and was not executed. | Not Executed
39 | TC_039 | UI | Verify that text and controls do not overlap. | 1. Open DemoBlaze. 2. Check layout at different sizes. | Different viewport sizes | Text and controls should not overlap. | Responsive/layout verification was not fully executed. | Not Executed
40 | TC_040 | Compatibility | Verify that the website works correctly in another browser. | 1. Open DemoBlaze in another browser. 2. Check core pages. | Another browser | Core pages should work consistently. | Cross-browser execution was not performed. | Not Executed

## DefectReport
Bug ID | BUG_001
Test Case ID | TC_016
Module | Cart
Application | DemoBlaze
Environment | Public DemoBlaze web page
Bug Summary | Place Order button is displayed when the cart is empty
Steps to Reproduce | 1. Open DemoBlaze. 2. Open Cart without adding any product. 3. Check the cart contents and Place Order button.
Expected Result | Place Order should be disabled or hidden when there are no products in the cart.
Actual Result | The empty cart page shows no product rows but still displays the Place Order button.
Severity | Medium
Priority | Medium
Status | Open
Bug ID | BUG_002
Test Case ID | TC_020
Module | Order / Validation
Application | DemoBlaze
Environment | Public DemoBlaze web page
Bug Summary | Blank order-field validation requires interactive verification
Steps to Reproduce | 1. Open Cart. 2. Click Place Order. 3. Leave all order fields blank. 4. Click Purchase.
Expected Result | Clear validation should be displayed and the order should not be completed.
Actual Result | Not verified in this execution.
Severity | Medium
Priority | Medium
Status | To Be Verified

## SummaryReport
Summary Report
Application | DemoBlaze
Application URL | https://www.demoblaze.com/
Testing Type | Manual Testing
Total Test Cases | 40
PASS | 21
FAIL | 1
NOT EXECUTED | 18
Pass Percentage | 52.5%
Fail Percentage | 2.5%
Not Executed Percentage | 45%
Total Defects | 2
Open Defects | 1
Defects To Be Verified | 1
Overall Result | Partially Executed